Project Charter

Semantic Layer & Contextual Grounding for Agentic AI

A Reference Implementation and Point of View

| Project sponsor | Nawab — Enterprise AI Architect |
| --- | --- |
| Duration | 4 weeks |
| Team | 2 interns (Intern A, Intern B) + sponsor supervision (1-2 hrs/week) |
| Output classification | Reusable Accenture asset — client engagements, capability validation, and external thought leadership |

Document version 1.0 — to be reviewed and confirmed at kickoff

# Contents

| 1. Why this project exists | 8. Technology stack |
| --- | --- |
| 2. Objectives | 9. Weekly milestone plan |
| 3. Deliverables | 10. Roles and time commitment |
| 4. Scope | 11. Risks and mitigations |
| 5. Dataset specification | 12. Definition of done |
| 6. Evaluation query catalogue | 13. Post-project — how the asset gets used |
| 7. Success metrics | 14. Sign-off |

## 1. Why this project exists

Every enterprise AI engagement reaches the same architectural question within the first six weeks: how should we structure the semantic layer that grounds our agents in business context? The two dominant patterns — a metadata-driven JSON catalog with vector search, and a knowledge graph with typed relationships and traversal — both claim to be the right answer. There is no settled, evidence-based view of which performs better, under which conditions, at what cost.

This project produces that evidence. Two interns build both patterns on the same dataset, run them through the same evaluation harness, and produce a defensible Point of View that Accenture can use in client conversations, technical validations, and thought-leadership content.

The output is a reusable asset, not a learning exercise. Every deliverable is engineered to be picked up and used in a real engagement.

## 2. Objectives

| # | Objective | Why it matters |
| --- | --- | --- |
| O1 | Build two working semantic layer implementations (metadata JSON + knowledge graph) on a shared dataset | Real code, runnable demo |
| O2 | Quantify the contextual grounding effectiveness of each pattern across 50 representative queries | Empirical evidence beats opinion |
| O3 | Produce a written Point of View on when to use each pattern, when to combine them, and how to decide | Reusable in client conversations |
| O4 | Productize the evaluation harness as a dataset-agnostic tool | Reusable in every future engagement |
| O5 | Develop the interns into engineers with production-grade RAG, vector search, knowledge graph, and evaluation experience | Pipeline for full-time conversion |

## 3. Deliverables

Four artifacts. Each is a tangible engagement asset, not a slide deck.

### Deliverable 1 — Semantic Layer Reference Implementation (code)

A working, runnable codebase implementing both patterns on the same synthetic procurement dataset, with shared embedding model, shared LLM, and shared retrieval interface. Anyone on the team can clone the repo, run make demo, and see both patterns answering the same questions. Demo-ready for client conversations.

### Deliverable 2 — Contextual Grounding Evaluation Harness (code)

A scripted, repeatable evaluation framework with the 50 evaluation queries, the scoring methodology, the metrics calculation, and the comparison output. Dataset-agnostic by design — point it at a different dataset and a different query set and it produces a new comparison. This is the asset that gets re-used across future use cases and clients.

### Deliverable 3 — Point of View Document

A 15–20 page technical PoV titled “Semantic Layer Patterns for Agentic AI: When to Use Metadata, When to Use Knowledge Graph, When to Use Both.” Accenture-branded, written for a senior technical audience (CTO, Chief Data Officer, Enterprise AI Architect). Includes pattern comparison, empirical findings with charts, decision framework, recommended patterns by use case shape, and acknowledged limitations of the study.

### Deliverable 4 — Use Case Design Template

A one-page template that takes use case properties (data volume, query types, multi-hop reasoning frequency, freshness needs) as inputs and outputs a recommended semantic layer pattern and configuration. Designed for use during discovery phases in any client engagement to compress what is typically a 3-week design debate into a 30-minute decision.

## 4. Scope

### In scope

- Two semantic layer patterns: metadata JSON catalog + knowledge graph

- Synthetic procurement dataset (English only)

- 50 evaluation queries across 5 categories

- Standard open-source technology stack

- Comparative evaluation with quantified metrics

- Written PoV and reusable templates

### Out of scope

- Multilingual support (English only for this iteration)

- Real client data (synthetic only, generated under controlled conditions)

- Production deployment, hardening, or operational concerns

- Comparison with proprietary commercial platforms

- Optimization beyond what is needed to fairly compare the two patterns

- Third semantic layer patterns (hybrid pattern noted as future work)

### Explicit exclusions

- This project does not recommend a single “winner.” The expected outcome is a decision framework, not a verdict.

- The knowledge graph schema design will be a competent first cut, not a domain-optimized production schema. This is acknowledged in the PoV.

## 5. Dataset specification

A synthetic procurement-shaped dataset, generated programmatically with LLM assistance, designed to be realistic in shape and volume.

### Dataset contents

| Entity type | Volume | Key attributes |
| --- | --- | --- |
| Suppliers | ~1,000 | ID, name, category, region, certifications, contract status, performance history |
| Catalog items | ~5,000 | ID, description, category, UNSPSC code, supplier link, price, attributes, status |
| Procurement policies | ~100 | ID, policy text, applicable categories, thresholds, approval routing, version |
| Contracts | ~50 | ID, supplier, items covered, term, pricing, tolerances |
| UNSPSC taxonomy | full | Hierarchical classification codes (Segment → Family → Class → Commodity) |
| Historical PO exceptions | ~500 | PO ID, reason, resolution, supplier, item |

### Why these volumes

Large enough to make retrieval non-trivial and to surface scaling effects. Small enough to run end-to-end on a single laptop or modest VM in under 10 minutes.

### Generation method

LLM-assisted synthetic generation with deterministic schemas, controlled randomness for realistic distributions, validation rules to ensure referential integrity (every catalog item links to a real supplier, every contract references real items, every policy applies to a real category).

### Why this matters

A weak dataset produces findings that don’t transfer. Week 1 is dedicated almost entirely to getting this right.

## 6. Evaluation query catalogue

50 queries across 5 categories. Each query has a known correct answer (or known set of acceptable answers) defined upfront by the team in Week 1.

| Category | Count | What it tests | Example |
| --- | --- | --- | --- |
| Direct retrieval | 10 | Baseline retrieval accuracy | “Find supplier records for IT services category” |
| Multi-hop reasoning | 15 | Following chains of relationships | “Which suppliers can fulfil this catalog item under our current contracts within applicable price tolerances?” |
| Filtered retrieval | 10 | Combining semantic and structured filters | “Find policies for IT equipment purchases over USD 100K issued after 2024” |
| Temporal reasoning | 5 | Versioning and time-based queries | “Find the policy that applied to procurement in Q2 2026” |
| Counterfactual / advisory | 10 | Reasoning about hypotheticals using context | “If we reject this PO, what’s the most likely reason based on similar past POs?” |

The expected outcome shape (not the verdict):

- Direct retrieval — both patterns perform comparably; baseline

- Multi-hop reasoning — knowledge graph likely outperforms

- Filtered retrieval — both perform well; latency differs

- Temporal reasoning — depends on schema design in both

- Counterfactual — hardest category for both patterns; useful failure analysis

## 7. Success metrics

Each query is scored across multiple dimensions. Each dimension is reported separately — there is no single composite score, because different use cases will weight these differently.

| Metric | Definition | Measurement |
| --- | --- | --- |
| Retrieval precision | Of items returned in top-K, what % are relevant | Manual relevance judgment on Week 1 ground truth |
| Retrieval recall | Of all relevant items in dataset, what % returned in top-K | Same |
| Reasoning accuracy | Does the agent reach the correct conclusion using retrieved context | Binary score against expected answer |
| Latency | Time from query to answer | Median and p95 in milliseconds |
| Token cost | LLM tokens consumed per query | Average per query |
| Build effort | Lines of code, time to add a new entity type, time to add a new relationship | Qualitative, recorded throughout |

### Success criteria for the project

| # | Criterion | Threshold |
| --- | --- | --- |
| S1 | Both implementations functional end-to-end | Both pass all 50 queries without crashing |
| S2 | Evaluation harness produces comparable results | All metrics computed for all queries on both patterns |
| S3 | At least 3 categories show statistically meaningful differences | p-value or effect size threshold defined in Week 1 |
| S4 | PoV document reviewed and approved by sponsor | Sign-off by end of Week 4 |
| S5 | Harness is demonstrably dataset-agnostic | Sponsor swaps in a different dataset slice in <30 min |

## 8. Technology stack

Standardised choices to remove confound variables and match typical enterprise patterns.

| Component | Choice | Why |
| --- | --- | --- |
| Vector store | Milvus (standalone mode) | Industry-standard, scales well, matches common enterprise platforms |
| Knowledge graph | Neo4j Community Edition | Industry standard, well-documented, free for prototype scale |
| Embedding model | intfloat/e5-large-v2 (English-only) | Strong English retrieval baseline, open-source, deterministic |
| LLM (generation) | OpenAI GPT-4o-mini via API, or Claude via API | Quality and consistency for fair comparison |
| Retrieval framework | LangChain (consistent across both implementations) | Reduces glue code, ensures comparable orchestration |
| Evaluation framework | RAGAS + custom scorers | Standard RAG evaluation; custom scorers for KG-specific metrics |
| Language / runtime | Python 3.11+ | Standard |
| Packaging | uv or poetry, Makefile, Dockerfile | One-command setup |
| Version control | Git, single repository, branching per intern | Standard |

Design principle: swappable components. All choices above are configured via environment variables or config files, so future iterations can swap the embedding model, LLM, vector store, or graph engine without touching application code.